## Sheet1
משימות |  |  | Column1
דיווחים | מצ"ב קובץ .ERRORS שיש להכניס כ-GET ID 100 | 1,5 h | 10 | 11.03 | V
הפעלה | in maintenance- inser reset (ID 63,9) | 1h | 10 | 11.03 | V
הפעלה | - ID 63.0\1- dont send "get" (maintenance) | 2h | 10 | 7.03 | V
דיווחים | detect no connection (1[0]=? -> motor status) ping | 2h | 10 | 13.03 | V
הפעלה | - refresh very slow | 3 days | 10
תצוגה | make tab color more intense when it opened | 3h | 5 | 11.03 | V
תצוגה | - change ON\OFF button | 2h | 5 | 11.03
תצוגה | open parameters window on main screen (same monitor as main window) | 5h | 2 | 14.03 | V
תצוגה | delet arrow of combobox in main screen- motion status | 3h | 2 | 14.03 | V
תצוגה | when click on float number it doesn’t select all the number | 4h | 2 | 13.03 | V
יחידות plot | add unit measure on graph (right side) | 2 days | 10 | 17.03 | V
| send 2 times the set in combobox |  | 10
| mtion command - signal generator no send operation |  |  |  | V
| 50[3] 50 [4] start 0 |  |  |  | V
| current [A] motion command, feedbak not correct |  |  |  | x
| VDC Motor get data of PowerSupply - yoav |  |  |  | V
| graph default x scale need to start at 0 - 1000 |  |  |  | x
| parameter PID kick out [A] | done
| - GUI sends on enable refresh ID 62.0- cancel it | done
| - PID tab- kick out current Kc | done
| - ID 63.10 check that its Int on GUI | done
| - ID index mode 71 7 | done
| gets enum (not float) | done
| - PID kick out Kc | done
| - some values doesn’t show anything when they not declered | done
| - RESET button in maintenance | done
| - in control tab- returning to forse-rotate | done