## GUI tasks
category | Task | Description | יוסף | שלומי | יחזקל | יואב | יבכני | עדיפות | Notes | Status
Functions | Import/Export parameters to file |  | 2 |  | 1 | 2 |  | 9 | bug
Functions | Import export QA | test 3 motor configurations, on 3 computers |  |  | 1 |  |  | 9
Functions | Debug window- erase one box |  | 1
Graph | Resume graph in reset | [6 empty] | 9 |  | done
Command | 12[0] On/Off "Power out 1" |  |  |  | 1 |  |  |  | QA only
Logger | ID 100 Reset notification |  |  |  | 1 |  |  | 9
Logger | Show locked baud on new conection | [6 empty] | 9 |  | done
Text box | (-) bug | Cannot ad (-) to a number |  |  | 1 |  |  | 8.5
Text box | red box should disable refrash | disable refrash only on specific box | [5 empty] | 8.5 |  | done
Calibrations | data refrash rate is low, should be 1 sec |  | 7 |  |  |  |  | 5
Command | Add comunication buad select in "device" |  |  |  | 1 |  |  | 8 | QA only
Graph | GUI install istructions | in user manual | 3 |  |  |  |  | 5
Conmmand | maintenance switches are not refrashed properlly | [6 empty] | 8 |  | done
Graph | Plot table | implemet at connction | 1 |  | 1 |  |  | 7 |  | in progress
Graph | Show real units on graph | [6 empty] | 7 |  | QA only
Graph | scop implementetion |  | 8 | 1
Serial loader | load firmware |  | 2 | 2 |  |  | 2 | 7
Visual | Driver Fail(From bottom panel to LeftPanel) PU |  | 0.5 |  |  |  |  | 7 |  | done
Graph | Improve graph flow | try new scichart and improve efficiently | ? | 1 |  |  |  | 7
Graph | 32 Bit postion/Speed | change protocol | 1 | 1 | 1 |  |  | 6
Logger | add comunications steps | [6 empty] | 6 | QA only
Logger | "OK" on Each comunication step | plot stage | 1 |  | 1 |  |  | 6
commands | Enum in Driver should be presented as enum | Such as "feedback Disbale/Enable" | [5 empty] | 6
Visual | improve design | improve visual design | 7 | 3 |  |  |  | 6
Functions | Com Disconnect/Reset QA |  |  |  | 1 |  |  | 5 | examples
Functions | Connot connect after baud change | [6 empty] | 7 | QA yy
feedbacks | Missing SSI commands | cancel ID 73 Idx 7 | 1 |  | 1 |  |  | 7
Visual | Black Icon |  | 0.2 |  |  |  |  | 8
Connect | show missing command responsess on log |  | 1.5 |  |  |  |  | 6
Logger | show colored packets |  | 2~ |  |  |  |  | 5
Motion | add startup enable |  | 1 |  | 1 |  |  | 7
Maintenance | Flash checksum | 62[10] (Show Data in HEX) | 1 |  |  |  |  | 7
Command | wrong enums in unit mode (ST speed?) | Remove all "ST xxxx" add "speed position" | 1 |  |  |  |  | 7
Visual | text should be with spaces | ADCoffset => ADC offset | 2 |  | 1 |  |  | 6
plot buttons work only if pressing twice |  |  | 1
QA new plot table protocol |  |  |  |  | 1
1
while connecting- plot table refreshing after 5 sec |  |  | 1
SUM |  |  | 0