## GUI tasks
category | Task | Description | יוסף | שלומי | יחזקל | יואב | יבכני | עדיפות | Notes | Status
Functions | Import/Export parameters to file review open files…path |  | 1 |  |  | 1 |  | 9 | bug
Functions | Import export QA | test 3 motor configurations, on 3 computers |  |  | 1 |  |  | 9
Functions | Debug window |  | 1.5 |  |  |  |  | 9
Command | power out put command 12[1] on/off int
Graph | Resume graph in reset | [6 empty] | 9
Logger | ID 100 Reset notification |  | 1 |  | 1 |  |  | 9
Logger | Show locked baud on new conection 460800 | [6 empty] | 9
Text box | (-) bug | Cannot ad (-) to a number | [5 empty] | 8.5
Text box | red box should disable refrash | disble refrash only on specific box | [5 empty] | 8.5
Calibrations | data refrash rate is low, should be 1 sec | [6 empty] | 8.5
Command | Add comunication buad select in "device" combobox | [6 empty] | 8
Graph | GUI install istructions | in user manual | 1 |  |  |  |  | 8
Conmmand | maintenance switches are not refrashed properlly | manufacture/save | [5 empty] | 8
Graph | Plot table | implemet at connction | [5 empty] | 7
Graph | Show real units on graph | [6 empty] | 7
Graph | left side and right side units | [6 empty] | 7
Serial loader | load firmware |  | 1 | 1 |  |  | 1 | 7
Commands | data refrash rate is low, should be 1 sec | [6 empty] | 7
Visual | Driver Fail(From bottom panel to LeftPanel) PU |  | 0.5 |  |  |  |  | 7
Graph | Improve graph flow |  | ? | 1 |  |  |  | 7
Graph | How to use Gui | in user manual | 1 |  | 1 |  |  | 6
Graph | 32 Bit postion/Speed | [6 empty] | 6
Logger | add comunications steps | [6 empty] | 6
Logger | "OK" on Each comunication step | [6 empty] | 6
commands | Enum in Driver should be presented as enum | Such as "feedback Disbale/Enable" | [5 empty] | 6
Visual | improve design |  | 1 |  |  |  |  | 6
Functions | Com Disconnect/Reset QA |  |  |  | 1 |  |  | 5